## Summary
AI Helpdesk - Phase 1 Requirements Tracker
Yellow cells are for you to edit (Priority, Status, Approval, Notes, Decisions). Counts below update automatically.
Requirements by priority | Count
Must (MVP) | 10
Should (v1.0) | 10
Could (later) | 0
Total | 20
Requirements by status | Count
Planned | 20
In Progress | 0
Implemented | 0
Tested | 0
Approval progress | Count
Requirements approved | 0
Open items unresolved | 8
Acceptance criteria done | 0
Acceptance criteria total | 5
Status key: Planned = not built yet. Only mark Implemented/Tested once code exists and tests were actually run.
Priority key: M = MVP (must ship), S = Should have (v1.0), C = Could have (later).

## Functional Requirements
# | Module | Requirement | Priority (M/S/C) | Status | Approval | Notes
1 | Auth | Sign up/in/out, secure sessions, password reset, email verification | M | Planned | Pending
2 | Authorization | Admin/Agent/Customer RBAC enforced server-side | M | Planned | Pending
3 | Tickets | Create, view, edit, close/reopen tickets | M | Planned | Pending
4 | Assignment | Assign/reassign to agent; 'unassigned' queue | M | Planned | Pending
5 | Status & priority | Statuses: Open, In Progress, Waiting on Customer, Resolved, Closed. Priorities: Low, Medium, High, Urgent | M | Planned | Pending
6 | Conversations | Threaded replies between customer and agents | M | Planned | Pending
7 | Internal notes | Agent-only notes, never visible to customers | M | Planned | Pending
8 | Categories | Admin-managed categories (e.g., Billing, Technical, Account) | M | Planned | Pending
9 | AI classification | Suggest category + priority on new tickets | S | Planned | Pending
10 | AI replies | Suggest a draft reply; agent must review before sending | S | Planned | Pending
11 | AI summaries | Summarize long threads | S | Planned | Pending
12 | Dashboard | Counts by status, avg first-response time, volume trend, agent workload | S | Planned | Pending
13 | Search/filter/sort | Full-text search; filter by status/priority/assignee/category/date | M | Planned | Pending
14 | Customer mgmt | Customer list, profile, ticket history | S | Planned | Pending
15 | Email notifications | Notify on new ticket, reply, assignment, status change | S | Planned | Pending
16 | Email-to-ticket | Inbound email creates or appends to a ticket | S | Planned | Pending
17 | Background jobs | Queue for emails, AI calls, inbound email processing, with retries | S | Planned | Pending
18 | Audit logs | Record who did what, when (role changes, assignment, deletes, logins) | S | Planned | Pending
19 | User mgmt | Admin creates/deactivates users, changes roles | M | Planned | Pending
20 | Deployment | Dockerized, CI/CD, hosted on Railway, monitored with Sentry | S | Planned | Pending

## Roles & Permissions
Role | Who they are | Can do | Cannot do
Customer | Person with an issue | Create tickets, view their own tickets, reply, see public replies only | See other customers' tickets, internal notes, AI output, audit logs
Agent | Support staff | View/work assigned and unassigned tickets, reply, add internal notes, change status/priority/category, use AI tools | Manage users, view system-wide audit logs, change system settings
Admin | Team lead / owner | Everything an agent can, plus user management, categories, analytics, audit logs, settings | Nothing is off-limits, but sensitive actions are audit-logged
All rules above must be enforced on the backend, not only hidden in the UI.

## Non-Functional
Area | Requirement | Status | Notes
Security | Server-side authorization on every endpoint, input validation (Zod), hashed passwords, secure cookies, rate limiting, no secrets in frontend, protection against OWASP Top 10 (injection, broken access control, XSS, CSRF) | Planned
Privacy | Customer data visible only to those who need it; AI prompts must not leak data across customers | Planned
Reliability | AI or email failures must never block ticket creation; failed jobs retry and are visible | Planned
Performance | Lists paginated; typical non-AI API response under ~300 ms (target to verify later, not a promise) | Planned
Accessibility | Keyboard navigable, sensible contrast and labels (WCAG 2.1 AA as the goal) | Planned
Maintainability | Strict TypeScript, modular code, consistent naming, tests on critical paths | Planned
Observability | Error tracking (Sentry), structured logs | Planned
Cost control | AI calls metered, limited per user/time, cached where safe | Planned

## AI Rules & Risks
Type | Item | Addressed in
Rule | AI assists, never acts alone: no auto-sending replies, no auto-closing tickets | Phase 3
Rule | Every AI output is labeled as AI-generated and is editable | Phase 3
Risk | Wrong classification | Phase 3
Risk | Hallucinated answers | Phase 3
Risk | Prompt injection from ticket text (customers can write anything) | Phase 3
Risk | PII sent to a third-party API | Phase 3

## Scope & Assumptions
Type | Item | Decision
Assumption | Single organization (one company's helpdesk), not multi-tenant SaaS | Pending
Assumption | Customers can self-register; agents/admins are created by an admin | Pending
Assumption | English only | Pending
Assumption | Transactional email provider (e.g., Resend or Postmark); final choice in Phase 3 | Pending
Assumption | File attachments not in MVP, added in v1.0 | Pending
Assumption | One ticket has one assignee at a time | Pending
Assumption | Free/low-tier hosting and a small OpenAI budget are acceptable | Pending
Out of scope | Live chat | Pending
Out of scope | Phone/voice | Pending
Out of scope | SLA contracts with breach automation | Pending
Out of scope | Multi-tenant / multi-company support | Pending
Out of scope | Knowledge-base portal | Pending
Out of scope | Mobile apps | Pending
Out of scope | Billing / subscriptions | Pending
Out of scope | File-attachment virus scanning (flagged as a decision) | Pending

## Open Items
# | Open item | Decision / answer | Resolved?
1 | File attachments: common in support; assumed v1.0. Confirm. |  | No
2 | Ticket lifecycle rules: who can reopen a closed ticket; auto-close after N days of silence? |  | No
3 | Notification preferences: can users opt out of emails? |  | No
4 | Data retention and deletion: soft vs. hard delete; 'delete my data' requests |  | No
5 | Rate limiting and abuse protection on public ticket creation and inbound email (spam) |  | No
6 | Email-to-ticket threading: how replies are matched to the right ticket (Phase 3 design) |  | No
7 | Verify current docs/versions of Better Auth, Prisma, Vercel AI SDK before locking the stack (Phase 3) |  | No
8 | Background jobs need Redis or a Postgres-based queue on Railway (Phase 3 decision) |  | No

## Phase 1 Acceptance
Acceptance criterion | Done?
Agree with the three roles and their permissions | No
Agree with the MVP / Should / Could split | No
Accepted or changed each assumption | No
Agree with the out-of-scope list | No
Open items have an answer or an explicit 'decide later' | No